## Slide 1: Effort Estimation Using Function Points

## Slide 2: Function Point Estimation
Function point estimation is a method for estimating the size and complexity of software systems based on the functionality provided to the user. Here's how it works:
Example: Building a Simple Web Application
Suppose you are tasked with estimating the effort required to develop a basic web application for a small e-commerce site. The application will have the following functionality:
User Registration.
User authentication (login, logout).
Product catalog browsing.
Adding products to the shopping cart.
Viewing the shopping cart.
Placing an order.
Review order status
..etc

## Slide 3: Step 1: Identify Functionality
First, identify the different types of functionality that the system will provide. In this case, we have identified five main functions:
User Registration
User authentication
Product catalog browsing
Adding products to the shopping cart
Viewing the shopping cart
Placing an order
…etc

## Slide 4: Step : Assign Function Points
Next, assign function points to each function based on its complexity and size. Function points are typically assigned on a scale from 0 to 5, with 0 being no complexity and 5 being very high complexity. For example:
User authentication: 3 function points
Product catalog browsing: 4 function points
Adding products to the shopping cart: 3 function points
Viewing the shopping cart: 2 function points
Placing an order: 4 function points

## Slide 5: Step 3: Calculate Total Function Points
Add up the function points for all functions to get the total function points for the project:
Total function points = 3 + 4 + 3 + 2 + 4 = 16 function points

## Slide 6: Step 4: Convert Function Points to Effort
Use a conversion factor to convert function points to effort. This conversion factor is based on historical data or industry standards.
For example, let's say the conversion factor is 20 hours per function point:
Total effort = Total function points * Conversion factor = 16 function points * 20 hours/function point = 320 hours
So, the estimated effort required to develop the web application is 320 hours.

## Slide 7: Step 5: Adjust for Complexity Factors
Finally, adjust the estimated effort based on complexity factors such as platform constraints, performance requirements, and development environment.
These factors can increase or decrease the estimated effort accordingly.

## Slide 8: Example
Feature/User Req. | Function point | Total Function Points (* 20) | # of Days
UR1 | 4 | 80 | 10
UR2 | 5 | 100 | 13
UR3 | 2 | 40 | 5
…. | … |  | 
Total | 32 | 640 | 80
We will need 4 months for one developer, 2 months for two developers and so on
Calculate the monthly or weekly salary of involved developers, example two developer that will work 100%, their salaries per month are 1400 + 1600 = $ 3000 is the cost of 2 developers per month.
Which means $ 6000 for two months.
Add the percentage of profit: min = 30%, max is 50% for example
So min offer is $7800 and max offer is $9000